## Sheet1
Customer Benefits | DM Area | TM Area | Post Code | Lat | Long | Project | Type | Total Spend | Customers Affected | Start Quarter | End Quarter | Duration
The completion of the this project will improve restoration times and limit customers affected by high voltage incidents. | Leicester & Kettering | Leicester & Kettering | Various |  |  | Cranoe Cct Slawston PMR, Slawston PMR, Marsh Drive Kibworth PMR, Woodhouse Eaves PMR, Uppingham Road Skeffington PMR, Bybrook PMR, Thorpe Langton PMR, Kilby Road Fleckney PMR, Ratcliffe Rd Thrussington PMR | Asset replacement on condition | 100000 | Rural Customers | Q1 2018 | Q4 2018 | 52 weeks
Reduction in the number of interruptions caused by trees. | Leicester & Kettering | Leicester & Kettering | Various |  |  | Annual Tree Cutting across Leicester & Kettering area | Resilience | 500000 | This will benefit all customers on rural networks | Q1 2017 | Q4 2017 | 52 weeks
Completion of this project will increase both the transfer capacity and reliability of the 33kV network in this area. | Leicester & Kettering | Leicester South | LE8 0HJ | 52.538783 | -1.018836 | Kibworth to Market Harborough | Asset replacement/Reinforcement | 5000000 | 14273 | Q3 2014 | Q2 2018 | 104 week
Completion of this project will increase security of the network for customers fed from Thurnby and Wigston Magna primary substations. | Leicester & Kettering | Leicester South | LE18 3QD | 52.584320 | -1.100606 | Wigston Magna to Oadby to Thurnby | Reinforcement | 1500000 | 1000 | Q2 2017 | Q2 2018 | 48 weeks
The integrity of the network will improve as well as increasing the security of supply. Overhead spans will be removed from oversailing the highway. | Leicester & Kettering | Leicester North | LE12 7JG | 52.723557 | -1.136967 | Danvers Road, Mountsorrel | Cable Undergrounding | 22239 | 9 | Q2 2018 | Q2 2018 | 4 weeks
Completion of this project will increase both the capacity and reliability of the 33kV network in this area. | Leicester & Kettering | Leicester North | LE12 6TD | 52.820481 | -1.065214 | Willoughby PSS to Mountsorrel PSS | Asset replacement/Reinforcement | 1000000 | 10471 | Q2 2013 | Q4 2018 | 64 weeks
Minimises the number of faults/interruptions caused by trees falling into the lines. | Leicester & Kettering | Leicester North | Various |  |  | Loughborough/Shepshed | Network Resilience | 120000 | This will benefit customers in the Shepshed area | Q2 2017 | Q2 2019 | 104 weeks
This project will increase the security of supply in Leicester City Centre and remove WPD assets from a historic and iconic building. | Leicester & Kettering | Leicester City | LE1 5GG | 52.634142 | -1.134279 | Leicester Corn Exhange | Asset replacement/Reinforcement | 85000 | 166 | Q4 2017 | Q2 2018 | 24 weeks
Completion of this project will increase the capacity, security and reliability of the LV network in this area. | Leicester & Kettering | Leicester City | LE3 0BQ | 52.630059 | -1.147819 | Narborough Road, Leicester | Reinforcement | 32750 | 1000 | Q4 2017 | Q2 2018 | 24 weeks
The completion of the this project will increase network security and fault response times. | Leicester & Kettering | Leicester City | LE1 3RW | 52.637228 | -1.129682 | Lee Circle, Leicester | Asset replacement/Reinforcement | 27965 | 32 | Q1 2018 | Q3 2018 | 18 weeks
The integrity of the network will improve as well as increasing the security of supply. Overhead spans will be removed from proximity to trees. | Leicester & Kettering | Kettering | LE16 8JZ | 52.424432 | -0.892255 | Bulls Head Inn, Arthingworth | Cable Undergrounding | 20461 | 6 | Q2 2018 | Q3 2018 | 4 weeks
The integrity of the network will improve as well as increasing the security of supply. | Leicester & Kettering | Kettering | NN17 3JY | 52.493261 | -0.635619 | Church Street, Weldon | Asset replacement on condition | 19463 | 62 | Q3 2017 | Q1 2018 | 10 weeks
This project will improve the fault response times and therefore reduce the duration of customer outages when a fault occurs. The replacement of older switchgear will also reduce the number of faults experienced. | Leicester & Kettering | Kettering | NN16 8UG | 52.398080 | -0.737885 | Grasmere Road, Kettering | Asset Replacement/Reinforcement/Automation | 74321 | 170 | Q1 2017 | Q1 2018 | 32 weeks
This would improve system security and to accommodate an improved feeding arrangement for recently connected generation. | Leicester & Kettering | North East Northants | NN9 5QU | 52.319757 | -0.616181 | Irthlingborough/Thrapston | Asset replacement/Reinforcement | 2,200,000-2,500,000 | 4800 | Q3 2013 | Q2 2018 | 204 weeks
This project will improve the reliabilty of the asset and network security. | Leicester & Kettering | North East Northants | NN14 3DZ | 52.411984 | -0.442613 | Crows Nest Farm, Clopton, Northants | Asset replacement on condition | 123807 | 10 | Q2 2017 | Q3 2017 | 8 weeks
This project will improve the reliabilty of the asset and network security. | Leicester & Kettering | North East Northants | NN8 4DS | 52.305410 | -0.689656 | Cannon Street, Wellingborough | Asset replacement/Reinforcement | 95649 | 758 | Q2 2017 | Q2 2017 | 4 weeks
This project will improve the fault response times (owing to automation) and the ability to switch around the HV network. Therefore reduce the duration of customer outages when a fault occurs. | Leicester & Kettering | North East Northants | NN9 6BB | 52.330709 | -0.506256 | Mere Farm, Hargrave, Northants | Reinforcement | 6274 | 31 | Q4 2017 | Q4 2017 | 1 week
The integrity of the network will improve as well as increasing the security of supply. | Leicester & Kettering | North East Northants | MK44 1JP | 52.225643 | -0.553385 | Lodge Road, Sharnbrook | Asset replacement on condition | 3876 | 80 | Q4 2017 | Q4 2017 | 2 weeks