## Sheet1
Customer Benefits | DM Area | TM Area | Post Code | Lat | Long | Project | Type | Total Spend | Customers Affected | Start Quarter | End Quarter | Duration
greater security of supply to customers in the area, creates capacity in the network to allow for load growth in the surrounding areas. | Nottingham | Nottingham west | NG16 1LA | 53.006919 | -1.252311 | Watnall and surrounding areas | 33kv & 11kv reinforcement | 5000000 | 10000 | Q1 2015 | Q4 2017 | 3 years
Greater security of supply to customers in the area, and reduction in supply interruptions. | Nottingham | Nottingham East | NG14 6NR | 53.041992 | -1.101179 | Hucknall - Calverton | 33kV overhead line rebuild | 325000 | 23000 | Q2 2018 | Q3 2018 | 3 months
Greater security of supply to customers in the area, and reduction in supply interruptions. Of particular benefit to rural areas. | Nottingham | Nottingham East | NG14 6ED | 53.025925 | -1.071455 | Woodborough Interconnection | 11kV reinforcement - interconnection | 75000 | 3200 | Q1 2018 | Q2 2018 | 2 months
Increased secure backfeeding capacity for the new developmenta and surrounding area. | Nottingham | Nottingham West | NG16 1HY | 53.016669 | -1.233450 | Watnall to Hucknall Feeder Overlay | 11kV Network Reinforcement- New Connection | 234555 | 1500+ | Q2 2018 | Q2 2019 | 12 months
Increased secure backfeeding capacity for the new development and surrounding area at 11kV and LV. | Nottingham | Nottingham City | NG1 7LL | 52.950210 | -1.147645 | The Broadmarsh Centre Redevelopment | 11kV & LV Network Reinforcement - New Connection | 177548 | 1327 | Q4 2017 | Q3 2020 | 3 years
Increased secure backfeeding capacity for the new development and surrounding area. | Nottingham | Nottingham City | NG2 3GZ | 52.945638 | -1.133210 | Crocus Street Development | 11kV Network Reinforcement - New Connection | 327771 | 2888 | Q2 2018 | Q4 2019 | 18 months
Development of EV charging on the network throughout the city of Nottingham to assist with facilitating low carbon verhicles. | Nottingham | Nottingham City | NG1 2DT | 52.953466 | -1.149069 | Go Ultra Low EV Charger Infrastructure | Innovative Project - Study |  |  | Q1 2017 |  | Ongoing
Removal of fault level restrictions applied to Lenton Primay Substation to facilitate the connection of low carbon technology. | Nottingham | Nottingham City | NG7 2EB | 52.945432 | -1.186685 | University of Nottingham University Park Switchgear Change | 11kV Switchgear Replacement | 184000 | 1563 | Q2 2018 | Q4 2018 | 6 months
Increased reverse power flow capacity at Chilwell Primay Substation to facilitate the connection of low carbon technology. | Nottingham | Nottingham West | NG9 5BL | 52.916675 | -1.228672 | Chillwell Primary Reverse Power Flow Reinforcements | Protection Replacement Scheme - New Connection | 18489 | 9037 | Q2 2017 | Q4 2017 | 6 months
This will reduce the number of customer minutes lost in the event of network faults by allowing implimentation of sequence schemes and switch remotely to restore power in a target of under 3 minutes. | Nottingham | Nottingham | (Throughout District) |  |  | Automation | Network Automation | 158000 | Unknown | Q1 2018 | Q4 2018 | 12 months
This will help reduce the number and legth of interruptions to shops and customers around the Old Market Square. | Nottingham | Nottingham City | NG1 2DR | 52.953895 | -1.149969 | Old Market Square | Asset Replacement | 100000 | 700 | Q2 2018 | Q4 2018 | 6 Months
The replacement of the cable is due to age and condition and will reduce the number of interruptions customers were seeing and the new switching station will enable customers to be restored quicker if there are further faults on the 11kv network. | Nottingham | Nottingham City | NG2 5AX | 52.938014 | -1.102844 | Holme Pierrepont and West Bridgford | Asset replacement and Worst served customer | 35000 | 1800 | Q1 2017 | Q2 2017 | 3 Months